## 01 Executive Summary
CostProof — finance model
The output of a causal cost-measurement engine, delivered as an FP&A workbook.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
The problem
Every cloud cost tool reports what was spent. None can prove what an optimisation saved,
because teams act on spikes and spikes revert on their own. Before/after comparison
credits the team for gravity. This workbook shows what changes when the saving is
measured against a control group instead.
Two workbooks, two questions
costproof-business-case.xlsx asks: should an organisation buy the measurement layer?
Its NPV counts only decision quality -- effort not wasted on fixes that did nothing.
This workbook asks: what did the optimisation programme itself deliver, measured
properly, and what is that worth? Its savings are the cloud savings; its costs are the
engineering to achieve them plus the team that measures them. Different question,
different NPV. Neither is the other one restated.
Headline figures (formulas; active scenario)
Measure | Value | Where it comes from
Events measured | 117 | Savings Attribution
Passing the parallel-trends check | 103 | Savings Attribution
Before/after would report, per year | 1693741.0017 | Savings Attribution — the industry's number
Credited savings, per year | 1872634.0413 | Savings Attribution — identified, gated
Difference the method makes | 178893.0396 | ROI Analysis
Programme NPV, five years | 2833109.4303 | ROI Analysis
Benefit-to-cost ratio | 2.8634 | ROI Analysis
Payback, months | 6.5471 | ROI Analysis
Budget variance over the period | 7.198% | Budget vs Actual
SIMULATED: gross misattribution in before/after | 450967.8445 | Savings Attribution — needs ground truth
Active scenario / attribution policy | Base / PT gate | Assumptions
How to read this workbook
Blue cells are inputs; black cells are formulas; green cells link to another sheet.
Only estimates that pass the parallel-trends check are credited, unless you flip the
policy switch on Assumptions. Bear/Bull/Base are execution scenarios, not measurement
scenarios: the estimator's own error is quantified on Savings Attribution.
Peach cells use simulated ground truth. They are the reason the method can be
validated here and the reason it would be needed on real data, where they do not exist.
Sheets
02 Raw Cost Data |  | monthly cost by business unit; the pivot is formulas
03 Optimization Events |  | the intervention register
04 Savings Attribution |  | per-event estimates, the gate, the credited total
05 Budget vs Actual |  | run-rate budget vs actual, by unit and month
06 Forecast |  | twelve months forward, two methods
07 ROI Analysis |  | programme cash flows, NPV, ROI, IRR, payback
08 Scenario Analysis |  | Base / Bull / Bear side by side
09 Sensitivity Analysis |  | NPV grids over four drivers
10 Assumptions |  | every input, in one place
11 KPI Dashboard |  | tiles and charts
Generated by scripts/build_finance_model.py from the pipeline's own outputs. Regenerate after `costproof study`; nothing here is typed in.

## 02 Raw Cost Data
Raw cost data
Monthly effective, billed and list cost by business unit, from the silver layer (Usage rows, complete months only). The pivot on the right is formulas.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Effective cost by month and business unit (SUMIFS over the table)
Month | Business unit | Effective cost | Billed cost | List cost | Month | # | bu-assist | bu-checkout | bu-datalake | bu-datasci | bu-platform | bu-search | unallocated | Total
2025-01-01 | bu-assist | 141869.6298 | 116240.3917 | 158448.0423 | 2025-01-01 | 1 | 141869.6298 | 77461.639 | 57576.4215 | 114791.873 | 70348.9182 | 80411.6905 | 69283.9208 | 611744.0928
2025-01-01 | bu-checkout | 77461.639 | 45232.6143 | 93014.0084 | 2025-02-01 | 2 | 131285.9651 | 71395.969 | 55351.0382 | 129367.1026 | 68187.3582 | 75021.547 | 64715.5959 | 595324.576
2025-01-01 | bu-datalake | 57576.4215 | 47000.0251 | 64010.9315 | 2025-03-01 | 3 | 170694.1138 | 87880.4923 | 61084.4258 | 199666.197 | 69367.6651 | 87877.0547 | 75572.938 | 752142.8866
2025-01-01 | bu-datasci | 114791.873 | 112932.9282 | 118048.3077 | 2025-04-01 | 4 | 173641.1952 | 91758.2873 | 68648.7447 | 155580.0794 | 72773.1213 | 89750.9764 | 73834.6768 | 725987.0813
2025-01-01 | bu-platform | 70348.9182 | 59598.3076 | 77787.2282 | 2025-05-01 | 5 | 168584.8629 | 96378.5621 | 70552.1758 | 161497.2725 | 72013.672 | 94285.1147 | 84541.5329 | 747853.1929
2025-01-01 | bu-search | 80411.6905 | 63621.6195 | 91372.071 | 2025-06-01 | 6 | 157180.4365 | 92478.4185 | 70541.8285 | 140313.553 | 73722.1747 | 90268.7341 | 77440.757 | 701945.9023
2025-01-01 | unallocated | 69283.9208 | 50164.5248 | 79175.3078 | 2025-07-01 | 7 | 157484.6965 | 93742.4528 | 71220.4689 | 154568.5751 | 70392.8494 | 97421.9546 | 78358.7276 | 723189.7249
2025-02-01 | bu-assist | 131285.9651 | 108775.4363 | 145911.6073 | 2025-08-01 | 8 | 164579.1068 | 97362.1618 | 63816.123 | 143516.3148 | 73737.5983 | 100098.4352 | 77229.2808 | 720339.0207
2025-02-01 | bu-checkout | 71395.969 | 40575.8107 | 85967.4846 | 2025-09-01 | 9 | 158979.4144 | 92261.5062 | 61211.5172 | 159667.5958 | 77160.9571 | 95928.8624 | 81095.158 | 726305.0112
2025-02-01 | bu-datalake | 55351.0382 | 45654.6645 | 61360.8553 | 2025-10-01 | 10 | 173558.5418 | 111068.9696 | 61411.7857 | 164202.5117 | 87267.349 | 109009.5874 | 85190.819 | 791709.5642
2025-02-01 | bu-datasci | 129367.1026 | 127972.2208 | 132211.3708 | 2025-11-01 | 11 | 170043.1224 | 132965.7974 | 58841.3899 | 144469.2641 | 85378.4664 | 119213.6236 | 90806.4504 | 801718.1142
2025-02-01 | bu-platform | 68187.3582 | 57902.0044 | 75400.1806 | 2025-12-01 | 12 | 196719.2147 | 126834.2342 | 67374.5645 | 179764.6248 | 77821.1707 | 113922.0861 | 93942.017 | 856377.9119
2025-02-01 | bu-search | 75021.547 | 59454.2061 | 85035.7863 | 2026-01-01 | 13 | 198025.435 | 102962.322 | 68852.6929 | 181287.5053 | 78034.4955 | 92404.9375 | 83037.662 | 804605.0502
2025-02-01 | unallocated | 64715.5959 | 47816.9797 | 73676.6353 | 2026-02-01 | 14 | 172349.5835 | 93784.6565 | 64577.3672 | 145215.4029 | 67682.0376 | 87466.7319 | 77358.6495 | 708434.4292
2025-03-01 | bu-assist | 170694.1138 | 143497.1648 | 188887.4939 | 2026-03-01 | 15 | 207714.8918 | 107075.4452 | 74857.5749 | 219042.9453 | 74464.0145 | 100600.7407 | 86338.6019 | 870094.2144
2025-03-01 | bu-checkout | 87880.4923 | 51607.7945 | 105580.5139 | 2026-04-01 | 16 | 215101.3348 | 99504.5953 | 78120.4239 | 239549.4396 | 72718.1095 | 94561.9203 | 81252.9156 | 880808.739
2025-03-01 | bu-datalake | 61084.4258 | 49295.2738 | 68135.7045 | 2026-05-01 | 17 | 199289.5748 | 107902.8159 | 79901.8988 | 182830.5607 | 77319.3466 | 102550.6498 | 87225.1647 | 837020.0112
2025-03-01 | bu-datasci | 199666.197 | 197792.7352 | 203002.0344 | Total |  | 2957101.1197 | 1682818.3251 | 1133940.4414 | 2815330.8175 | 1268389.3044 | 1630794.647 | 1367224.8678 | 12855599.5229
2025-03-01 | bu-platform | 69367.6651 | 56372.5953 | 77787.4875
2025-03-01 | bu-search | 87877.0547 | 69395.7018 | 99862.8396 | Effective cost is used throughout: it amortises commitments across the period they cover. Billed cost would show prepaid resources as free.
2025-03-01 | unallocated | 75572.938 | 57307.5974 | 85723.9921
2025-04-01 | bu-assist | 173641.1952 | 147917.6227 | 190473.9476
2025-04-01 | bu-checkout | 91758.2873 | 51592.344 | 110942.4627
2025-04-01 | bu-datalake | 68648.7447 | 54663.8544 | 76776.671
2025-04-01 | bu-datasci | 155580.0794 | 153718.3581 | 158961.843
2025-04-01 | bu-platform | 72773.1213 | 60406.6943 | 81046.8205
2025-04-01 | bu-search | 89750.9764 | 69717.8222 | 102308.9699
2025-04-01 | unallocated | 73834.6768 | 56369.364 | 83769.1309
2025-05-01 | bu-assist | 168584.8629 | 143013.3982 | 185353.0925
2025-05-01 | bu-checkout | 96378.5621 | 54302.4436 | 116714.1885
2025-05-01 | bu-datalake | 70552.1758 | 55686.552 | 79130.7459
2025-05-01 | bu-datasci | 161497.2725 | 159412.5764 | 165662.2027
2025-05-01 | bu-platform | 72013.672 | 59871.7359 | 80063.3666
2025-05-01 | bu-search | 94285.1147 | 72445.4544 | 108067.3143
2025-05-01 | unallocated | 84541.5329 | 65543.1034 | 95243.0015
2025-06-01 | bu-assist | 157180.4365 | 129413.1125 | 174098.4164
2025-06-01 | bu-checkout | 92478.4185 | 51640.4265 | 111803.0585
2025-06-01 | bu-datalake | 70541.8285 | 54665.0468 | 79795.5001
2025-06-01 | bu-datasci | 140313.553 | 138631.3303 | 143918.4624
2025-06-01 | bu-platform | 73722.1747 | 62466.2342 | 81422.7963
2025-06-01 | bu-search | 90268.7341 | 71331.2117 | 102918.6826
2025-06-01 | unallocated | 77440.757 | 58848.6949 | 87835.232
2025-07-01 | bu-assist | 157484.6965 | 123940.3666 | 177246.9646
2025-07-01 | bu-checkout | 93742.4528 | 55827.1057 | 111491.0378
2025-07-01 | bu-datalake | 71220.4689 | 56567.6088 | 80130.1094
2025-07-01 | bu-datasci | 154568.5751 | 153074.0748 | 158076.5049
2025-07-01 | bu-platform | 70392.8494 | 58376.6192 | 78205.8584
2025-07-01 | bu-search | 97421.9546 | 78468.5264 | 110277.9608
2025-07-01 | unallocated | 78358.7276 | 60000.2485 | 88971.9786
2025-08-01 | bu-assist | 164579.1068 | 130479.7669 | 185215.0175
2025-08-01 | bu-checkout | 97362.1618 | 59332.7082 | 115549.6328
2025-08-01 | bu-datalake | 63816.123 | 50925.5783 | 71607.4904
2025-08-01 | bu-datasci | 143516.3148 | 142232.9508 | 146685.6833
2025-08-01 | bu-platform | 73737.5983 | 60239.5788 | 82354.1714
2025-08-01 | bu-search | 100098.4352 | 80096.2584 | 113127.8967
2025-08-01 | unallocated | 77229.2808 | 58015.9785 | 88522.0149
2025-09-01 | bu-assist | 158979.4144 | 127236.9307 | 178684.8792
2025-09-01 | bu-checkout | 92261.5062 | 55425.1952 | 109935.3339
2025-09-01 | bu-datalake | 61211.5172 | 50271.3942 | 68009.7254
2025-09-01 | bu-datasci | 159667.5958 | 158193.3501 | 162804.7979
2025-09-01 | bu-platform | 77160.9571 | 59407.5648 | 86729.7769
2025-09-01 | bu-search | 95928.8624 | 76748.6268 | 108591.7693
2025-09-01 | unallocated | 81095.158 | 63457.1598 | 92406.3144
2025-10-01 | bu-assist | 173558.5418 | 136182.027 | 197108.4305
2025-10-01 | bu-checkout | 111068.9696 | 64781.4227 | 132050.7694
2025-10-01 | bu-datalake | 61411.7857 | 49947.3236 | 68383.8801
2025-10-01 | bu-datasci | 164202.5117 | 162924.4632 | 167402.1189
2025-10-01 | bu-platform | 87267.349 | 65003.4161 | 98076.2702
2025-10-01 | bu-search | 109009.5874 | 87557.6061 | 123405.8492
2025-10-01 | unallocated | 85190.819 | 65774.9221 | 96857.4351
2025-11-01 | bu-assist | 170043.1224 | 130034.2035 | 194390.3133
2025-11-01 | bu-checkout | 132965.7974 | 74556.6364 | 158295.1844
2025-11-01 | bu-datalake | 58841.3899 | 47089.6044 | 65802.2951
2025-11-01 | bu-datasci | 144469.2641 | 143095.1958 | 147611.0744
2025-11-01 | bu-platform | 85378.4664 | 65911.378 | 95384.5071
2025-11-01 | bu-search | 119213.6236 | 94714.8066 | 135350.0758
2025-11-01 | unallocated | 90806.4504 | 68318.8225 | 103661.448
2025-12-01 | bu-assist | 196719.2147 | 159044.6949 | 219927.484
2025-12-01 | bu-checkout | 126834.2342 | 72387.0527 | 151140.0174
2025-12-01 | bu-datalake | 67374.5645 | 53509.9743 | 75479.7495
2025-12-01 | bu-datasci | 179764.6248 | 178090.3809 | 183337.4438
2025-12-01 | bu-platform | 77821.1707 | 61296.9465 | 86786.8869
2025-12-01 | bu-search | 113922.0861 | 88797.3892 | 130059.53
2025-12-01 | unallocated | 93942.017 | 71996.7956 | 106515.1267
2026-01-01 | bu-assist | 198025.435 | 169909.1631 | 216391.2902
2026-01-01 | bu-checkout | 102962.322 | 57731.5805 | 122746.3898
2026-01-01 | bu-datalake | 68852.6929 | 54855.2847 | 77099.2392
2026-01-01 | bu-datasci | 181287.5053 | 179895.1036 | 184496.2245
2026-01-01 | bu-platform | 78034.4955 | 66027.6045 | 86195.2652
2026-01-01 | bu-search | 92404.9375 | 70918.1555 | 106040.7176
2026-01-01 | unallocated | 83037.662 | 65844.5364 | 93982.5188
2026-02-01 | bu-assist | 172349.5835 | 144154.56 | 190284.295
2026-02-01 | bu-checkout | 93784.6565 | 49994.1532 | 112347.3348
2026-02-01 | bu-datalake | 64577.3672 | 51930.5607 | 72157.4017
2026-02-01 | bu-datasci | 145215.4029 | 143681.3377 | 148333.4049
2026-02-01 | bu-platform | 67682.0376 | 56172.1103 | 75315.444
2026-02-01 | bu-search | 87466.7319 | 66130.5348 | 101117.9626
2026-02-01 | unallocated | 77358.6495 | 61960.404 | 87825.264
2026-03-01 | bu-assist | 207714.8918 | 177468.3556 | 227637.3518
2026-03-01 | bu-checkout | 107075.4452 | 59140.7255 | 127710.0238
2026-03-01 | bu-datalake | 74857.5749 | 63181.6723 | 82531.1938
2026-03-01 | bu-datasci | 219042.9453 | 217498.9968 | 222594.0249
2026-03-01 | bu-platform | 74464.0145 | 60471.9546 | 83173.8922
2026-03-01 | bu-search | 100600.7407 | 77591.9142 | 115434.5626
2026-03-01 | unallocated | 86338.6019 | 69572.5198 | 98117.1431
2026-04-01 | bu-assist | 215101.3348 | 186553.9941 | 233824.5935
2026-04-01 | bu-checkout | 99504.5953 | 59315.5285 | 117975.1366
2026-04-01 | bu-datalake | 78120.4239 | 65624.4763 | 86167.5983
2026-04-01 | bu-datasci | 239549.4396 | 238046.6361 | 243206.159
2026-04-01 | bu-platform | 72718.1095 | 58953.9225 | 81202.7906
2026-04-01 | bu-search | 94561.9203 | 73870.1336 | 107994.4323
2026-04-01 | unallocated | 81252.9156 | 65681.1379 | 92140.1449
2026-05-01 | bu-assist | 199289.5748 | 170889.3116 | 217812.3693
2026-05-01 | bu-checkout | 107902.8159 | 64953.9445 | 127599.8665
2026-05-01 | bu-datalake | 79901.8988 | 66706.3585 | 88272.9797
2026-05-01 | bu-datasci | 182830.5607 | 181371.4603 | 186471.7529
2026-05-01 | bu-platform | 77319.3466 | 62572.919 | 86568.1244
2026-05-01 | bu-search | 102550.6498 | 82349.3498 | 115975.6672
2026-05-01 | unallocated | 87225.1647 | 71175.9956 | 98652.2463

## 03 Optimization Events
Optimisation events
Every intervention the study measured: what was done, to which resource, when, and what it was costing beforehand. The register the attribution sheet reads.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Events by action
Event | Resource | Business unit | Action | Action date | Trigger z | Donors | Pre-period daily run-rate | Annualised run-rate | Action | Count | Annualised run-rate
i-114 | r-0026 | bu-search | delete_orphaned_volume | 2025-05-02 | 2.3955 | 40 | 125.3463 | 45751.417 | cache_inference_results | 20 | 724939.6819
i-028 | r-0059 | bu-datasci | delete_orphaned_volume | 2025-05-16 | 0.71198 | 40 | 20.0565 | 7320.639 | consolidate_cluster | 14 | 408333.0943
i-088 | r-0260 | bu-platform | cache_inference_results | 2025-05-16 | 2.7694 | 40 | 8.843 | 3227.6889 | delete_orphaned_volume | 17 | 514985.1177
i-027 | r-0374 | bu-platform | cache_inference_results | 2025-05-16 | 0.72023 | 40 | 47.164 | 17214.8672 | enable_autoscaling | 13 | 497301.6296
i-030 | r-0097 | bu-checkout | enable_autoscaling | 2025-05-20 | 0.70693 | 40 | 66.6631 | 24332.0343 | migrate_storage_class | 17 | 831654.4264
i-049 | r-0372 | bu-checkout | cache_inference_results | 2025-05-24 | 0.63211 | 40 | 182.7168 | 66691.6417 | rightsize_instance | 14 | 409554.8679
i-029 | r-0164 | bu-platform | tune_batch_size | 2025-05-24 | 0.71166 | 40 | 24.7511 | 9034.1356 | schedule_shutdown | 12 | 403691.3125
i-011 | r-0352 | bu-datalake | consolidate_cluster | 2025-05-28 | 0.89202 | 40 | 64.2791 | 23461.8848 | tune_batch_size | 10 | 334141.6915
i-014 | r-0227 | bu-assist | migrate_storage_class | 2025-05-31 | 0.88304 | 40 | 445.0771 | 162453.1273 | Total | 117 | 4124601.8218
i-042 | r-0295 | bu-search | enable_autoscaling | 2025-06-07 | 0.65998 | 40 | 47.8779 | 17475.4415
i-067 | r-0307 | bu-assist | consolidate_cluster | 2025-06-14 | 0.44301 | 40 | 23.3122 | 8508.9576 | Run-rate = mean daily effective cost over the 84 days before the action, the same window the estimator uses.
i-093 | r-0155 | bu-assist | schedule_shutdown | 2025-06-16 | 2.6764 | 40 | 2.1084 | 769.5748
i-019 | r-0041 | bu-search | schedule_shutdown | 2025-06-17 | 0.79737 | 40 | 98.7295 | 36036.2826
i-043 | r-0375 | bu-platform | enable_autoscaling | 2025-06-18 | 0.65252 | 40 | 58.5616 | 21374.9756
i-034 | r-0314 | bu-assist | enable_autoscaling | 2025-06-20 | 0.69058 | 40 | 448.7834 | 163805.9489
i-055 | r-0376 | bu-datalake | cache_inference_results | 2025-06-20 | 0.55398 | 40 | 193.6523 | 70683.0927
i-036 | r-0350 | bu-assist | rightsize_instance | 2025-06-23 | 0.6871 | 40 | 8.9017 | 3249.1386
i-003 | r-0092 | bu-checkout | delete_orphaned_volume | 2025-06-24 | 0.998 | 40 | 253.4304 | 92502.0889
i-111 | r-0282 | bu-checkout | rightsize_instance | 2025-07-03 | 2.432 | 40 | 14.8842 | 5432.7477
i-015 | r-0131 | bu-platform | enable_autoscaling | 2025-07-04 | 0.85325 | 40 | 8.1296 | 2967.2994
i-054 | r-0255 | bu-datalake | migrate_storage_class | 2025-07-08 | 0.5665 | 40 | 116.1016 | 42377.0795
i-090 | r-0000 | bu-search | migrate_storage_class | 2025-07-10 | 2.7565 | 40 | 69.7996 | 25476.859
i-097 | r-0005 | bu-platform | delete_orphaned_volume | 2025-07-14 | 2.5948 | 40 | 21.6331 | 7896.0818
i-075 | r-0021 | bu-platform | tune_batch_size | 2025-07-18 | 0.31861 | 40 | 19.631 | 7165.3189
i-070 | r-0022 | bu-search | migrate_storage_class | 2025-07-19 | 0.37778 | 40 | 41.505 | 15149.3389
i-079 | r-0169 | bu-datasci | consolidate_cluster | 2025-07-21 | 0.28352 | 40 | 66.725 | 24354.6118
i-005 | r-0371 | bu-platform | tune_batch_size | 2025-07-24 | 0.97918 | 40 | 46.3368 | 16912.9187
i-002 | r-0222 | bu-checkout | tune_batch_size | 2025-08-07 | 1.0063 | 40 | 31.7521 | 11589.5132
i-026 | r-0386 | bu-search | enable_autoscaling | 2025-08-08 | 0.72702 | 40 | 11.9153 | 4349.0941
i-076 | r-0251 | bu-datasci | rightsize_instance | 2025-08-20 | 0.31006 | 40 | 382.0138 | 139435.0317
i-056 | r-0339 | bu-search | migrate_storage_class | 2025-08-21 | 0.54827 | 40 | 20.337 | 7423.0138
i-035 | r-0043 | bu-platform | consolidate_cluster | 2025-08-23 | 0.68711 | 40 | 29.502 | 10768.2381
i-044 | r-0395 | bu-search | enable_autoscaling | 2025-08-28 | 0.64606 | 40 | 35.6358 | 13007.0611
i-094 | r-0206 | bu-platform | tune_batch_size | 2025-09-03 | 2.6672 | 40 | 167.4531 | 61120.3752
i-080 | r-0101 | bu-checkout | schedule_shutdown | 2025-09-06 | 0.2817 | 40 | 26.4817 | 9665.808
i-061 | r-0216 | bu-platform | delete_orphaned_volume | 2025-09-06 | 0.53129 | 40 | 3.0996 | 1131.3362
i-018 | r-0389 | bu-assist | rightsize_instance | 2025-09-07 | 0.80536 | 40 | 8.4131 | 3070.769
i-012 | r-0241 | bu-datalake | rightsize_instance | 2025-09-07 | 0.89147 | 40 | 118.3999 | 43215.9691
i-046 | r-0094 | bu-assist | rightsize_instance | 2025-09-10 | 0.63855 | 40 | 118.8853 | 43393.1482
i-087 | r-0105 | bu-checkout | migrate_storage_class | 2025-09-10 | 2.9007 | 40 | 293.6729 | 107190.5976
i-037 | r-0230 | bu-datalake | migrate_storage_class | 2025-09-11 | 0.68588 | 40 | 78.1699 | 28532.0075
i-059 | r-0007 | bu-checkout | migrate_storage_class | 2025-09-14 | 0.54058 | 40 | 3.7424 | 1365.9815
i-116 | r-0345 | bu-platform | schedule_shutdown | 2025-09-16 | 2.3809 | 40 | 39.8099 | 14530.6176
i-089 | r-0360 | bu-platform | migrate_storage_class | 2025-09-17 | 2.7591 | 40 | 17.1491 | 6259.4221
i-085 | r-0122 | bu-datalake | migrate_storage_class | 2025-09-18 | 0.16915 | 40 | 14.8061 | 5404.2321
i-086 | r-0331 | bu-datasci | consolidate_cluster | 2025-09-19 | 0.16746 | 40 | 222.1427 | 81082.081
i-001 | r-0018 | bu-assist | rightsize_instance | 2025-09-23 | 1.0186 | 40 | 175.4064 | 64023.3326
i-038 | r-0322 | bu-search | rightsize_instance | 2025-09-24 | 0.6791 | 40 | 25.7301 | 9391.4792
i-068 | r-0359 | bu-platform | tune_batch_size | 2025-09-25 | 0.43579 | 40 | 18.1236 | 6615.1218
i-102 | r-0269 | bu-assist | rightsize_instance | 2025-09-29 | 2.5177 | 40 | 59.6471 | 21771.2061
i-000 | r-0163 | bu-assist | rightsize_instance | 2025-10-01 | 1.0611 | 40 | 37.1809 | 13571.0434
i-041 | r-0012 | bu-platform | migrate_storage_class | 2025-10-01 | 0.66182 | 40 | 54.4419 | 19871.2887
i-110 | r-0143 | bu-platform | schedule_shutdown | 2025-10-02 | 2.4437 | 40 | 39.5981 | 14453.3067
i-109 | r-0187 | bu-platform | delete_orphaned_volume | 2025-10-05 | 2.4624 | 40 | 20.7636 | 7578.699
i-051 | r-0361 | bu-checkout | delete_orphaned_volume | 2025-10-14 | 0.57811 | 40 | 9.1467 | 3338.5637
i-058 | r-0306 | bu-platform | cache_inference_results | 2025-10-14 | 0.54542 | 40 | 22.3768 | 8167.5298
i-057 | r-0166 | bu-checkout | schedule_shutdown | 2025-10-17 | 0.54672 | 40 | 187.1345 | 68304.092
i-081 | r-0004 | bu-assist | enable_autoscaling | 2025-10-18 | 0.27251 | 40 | 3.2859 | 1199.351
i-004 | r-0388 | bu-search | rightsize_instance | 2025-10-26 | 0.98579 | 40 | 5.6936 | 2078.1554
i-092 | r-0334 | bu-search | delete_orphaned_volume | 2025-10-28 | 2.7008 | 40 | 3.3965 | 1239.7233
i-100 | r-0364 | bu-checkout | delete_orphaned_volume | 2025-10-31 | 2.5263 | 40 | 44.7051 | 16317.347
i-113 | r-0317 | bu-platform | cache_inference_results | 2025-11-05 | 2.4057 | 40 | 10.0993 | 3686.2502
i-017 | r-0356 | bu-checkout | cache_inference_results | 2025-11-08 | 0.81882 | 40 | 15.8578 | 5788.1073
i-112 | r-0073 | bu-checkout | consolidate_cluster | 2025-11-09 | 2.421 | 40 | 42.6152 | 15554.5516
i-048 | r-0125 | bu-search | delete_orphaned_volume | 2025-11-13 | 0.63392 | 40 | 22.0986 | 8066.005
i-077 | r-0243 | bu-search | enable_autoscaling | 2025-11-16 | 0.29871 | 40 | 183.9079 | 67126.3948
i-047 | r-0279 | bu-platform | schedule_shutdown | 2025-11-18 | 0.63678 | 40 | 125.7285 | 45890.8969
i-033 | r-0392 | bu-datalake | cache_inference_results | 2025-11-20 | 0.69279 | 40 | 22.6341 | 8261.4494
i-082 | r-0025 | bu-platform | rightsize_instance | 2025-11-22 | 0.24294 | 40 | 15.8969 | 5802.3592
i-078 | r-0316 | bu-datasci | delete_orphaned_volume | 2025-11-27 | 0.29345 | 40 | 22.7147 | 8290.8592
i-106 | r-0315 | bu-checkout | cache_inference_results | 2025-11-28 | 2.5012 | 40 | 27.4823 | 10031.0281
i-096 | r-0082 | bu-assist | cache_inference_results | 2025-11-29 | 2.6146 | 40 | 20.3634 | 7432.6589
i-098 | r-0014 | bu-checkout | cache_inference_results | 2025-12-11 | 2.5854 | 40 | 4.9813 | 1818.1866
i-009 | r-0212 | bu-search | rightsize_instance | 2025-12-12 | 0.90043 | 40 | 97.4379 | 35564.8197
i-064 | r-0284 | bu-checkout | consolidate_cluster | 2025-12-13 | 0.48417 | 40 | 21.7532 | 7939.9168
i-031 | r-0118 | bu-checkout | consolidate_cluster | 2025-12-15 | 0.70098 | 40 | 12.8747 | 4699.2734
i-074 | r-0233 | bu-search | enable_autoscaling | 2025-12-16 | 0.33947 | 40 | 82.8027 | 30223.0037
i-010 | r-0137 | bu-platform | tune_batch_size | 2025-12-19 | 0.8968 | 40 | 404.2836 | 147563.5106
i-022 | r-0391 | bu-assist | cache_inference_results | 2025-12-30 | 0.7792 | 40 | 501.9269 | 183203.3151
i-104 | r-0089 | bu-checkout | consolidate_cluster | 2025-12-31 | 2.5152 | 40 | 97.8716 | 35723.1327
i-040 | r-0219 | bu-datasci | enable_autoscaling | 2026-01-04 | 0.66355 | 40 | 368.3093 | 134432.9011
i-050 | r-0341 | bu-datalake | cache_inference_results | 2026-01-16 | 0.58972 | 40 | 308.1439 | 112472.5286
i-052 | r-0095 | bu-search | cache_inference_results | 2026-01-16 | 0.57126 | 40 | 38.3151 | 13985.0041
i-039 | r-0067 | bu-platform | schedule_shutdown | 2026-01-23 | 0.67386 | 40 | 142.8078 | 52124.8647
i-091 | r-0108 | bu-platform | migrate_storage_class | 2026-01-23 | 2.7061 | 40 | 1.316 | 480.3286
i-063 | r-0133 | bu-datasci | tune_batch_size | 2026-01-24 | 0.51267 | 40 | 4.1928 | 1530.3876
i-072 | r-0049 | bu-platform | cache_inference_results | 2026-01-28 | 0.36133 | 40 | 49.4661 | 18055.1267
i-020 | r-0062 | bu-checkout | delete_orphaned_volume | 2026-01-29 | 0.79552 | 40 | 247.823 | 90455.3813
i-032 | r-0056 | bu-datalake | cache_inference_results | 2026-02-02 | 0.69737 | 40 | 41.6226 | 15192.2543
i-103 | r-0304 | bu-assist | consolidate_cluster | 2026-02-10 | 2.5156 | 40 | 108.4337 | 39578.2949
i-025 | r-0096 | bu-checkout | schedule_shutdown | 2026-02-11 | 0.73788 | 40 | 189.4385 | 69145.0406
i-006 | r-0373 | bu-assist | migrate_storage_class | 2026-02-14 | 0.9635 | 40 | 987.4562 | 360421.4951
i-007 | r-0268 | bu-datasci | cache_inference_results | 2026-02-19 | 0.93044 | 40 | 60.6479 | 22136.4863
i-024 | r-0294 | bu-datalake | delete_orphaned_volume | 2026-02-20 | 0.75006 | 40 | 170.7662 | 62329.6698
i-107 | r-0208 | bu-platform | enable_autoscaling | 2026-02-24 | 2.4831 | 40 | 6.1451 | 2242.9771
i-095 | r-0165 | bu-assist | consolidate_cluster | 2026-02-25 | 2.6511 | 40 | 116.4909 | 42519.1642
i-073 | r-0298 | bu-search | consolidate_cluster | 2026-03-01 | 0.3403 | 40 | 33.2416 | 12133.1675
i-069 | r-0301 | bu-checkout | migrate_storage_class | 2026-03-07 | 0.42737 | 40 | 39.6733 | 14480.7663
i-008 | r-0107 | bu-checkout | migrate_storage_class | 2026-03-07 | 0.92004 | 40 | 59.1629 | 21594.4698
i-060 | r-0228 | bu-assist | tune_batch_size | 2026-03-08 | 0.54016 | 40 | 78.8083 | 28765.0369
i-105 | r-0213 | bu-platform | cache_inference_results | 2026-03-21 | 2.5025 | 40 | 55.3146 | 20189.8315
i-101 | r-0367 | bu-assist | delete_orphaned_volume | 2026-03-22 | 2.5191 | 40 | 296.8701 | 108357.5909
i-115 | r-0237 | bu-assist | delete_orphaned_volume | 2026-03-24 | 2.3896 | 40 | 39.935 | 14576.2623
i-062 | r-0042 | bu-assist | schedule_shutdown | 2026-03-29 | 0.5177 | 40 | 84.4503 | 30824.3679
i-083 | r-0024 | bu-search | schedule_shutdown | 2026-03-29 | 0.23576 | 40 | 120.7455 | 44072.1077
i-066 | r-0234 | bu-search | tune_batch_size | 2026-04-05 | 0.46752 | 40 | 120.1243 | 43845.373
i-099 | r-0296 | bu-platform | enable_autoscaling | 2026-04-12 | 2.5595 | 40 | 40.4525 | 14765.1469
i-065 | r-0048 | bu-datasci | migrate_storage_class | 2026-04-12 | 0.47318 | 40 | 14.2455 | 5199.6114
i-021 | r-0278 | bu-platform | cache_inference_results | 2026-04-13 | 0.79057 | 40 | 175.7578 | 64151.6059
i-045 | r-0154 | bu-checkout | delete_orphaned_volume | 2026-04-16 | 0.64437 | 40 | 40.0433 | 14615.7873
i-013 | r-0264 | bu-search | rightsize_instance | 2026-04-18 | 0.88639 | 40 | 53.5772 | 19555.668
i-053 | r-0176 | bu-search | cache_inference_results | 2026-04-20 | 0.56802 | 40 | 198.7699 | 72551.0286
i-023 | r-0138 | bu-assist | consolidate_cluster | 2026-04-22 | 0.77113 | 40 | 240.9942 | 87962.8729
i-016 | r-0226 | bu-checkout | consolidate_cluster | 2026-05-03 | 0.83168 | 40 | 38.4848 | 14046.9472
i-071 | r-0069 | bu-datalake | migrate_storage_class | 2026-05-07 | 0.36206 | 40 | 21.8488 | 7974.8072
i-084 | r-0147 | bu-search | delete_orphaned_volume | 2026-05-08 | 0.18067 | 40 | 69.0895 | 25217.666
i-108 | r-0087 | bu-search | schedule_shutdown | 2026-05-08 | 2.4683 | 40 | 48.9708 | 17874.353

## 04 Savings Attribution
Savings attribution
What each event is credited with, on what evidence. Before/after is what the industry reports; the identified estimate is difference-in-differences with randomisation inference; the parallel-trends check decides whether it is credible.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Peach columns use ground truth, which exists only because the estate is simulated. A real deployment would not have them -- that is the point of needing an estimator at all.
Event | Business unit | Action | Annualised run-rate | Before/after effect (log) | Before/after annual $ | Identified effect (log) | CI low | CI high | p-value | Parallel trends passed | Credited? | Identified annual $ | Credited annual $ | SIMULATED true effect (log) | SIMULATED true annual $ | ¦Before/after − true¦ | Null event?
i-114 | bu-search | delete_orphaned_volume | 45751.417 | -0.10183 | 4429.342 | -0.19259 | -36.85% | 7.738% | 0.17073 | TRUE | TRUE | 8014.6329 | 8014.6329 | 0 | 0 | 4429.342 | TRUE
i-028 | bu-datasci | delete_orphaned_volume | 7320.639 | -1.1111 | 4910.5959 | -1.1042 | -77.19% | -51.84% | 0.02439 | TRUE | TRUE | 4894.1385 | 4894.1385 | -0.94162 | 4465.619 | 444.9769 | FALSE
i-088 | bu-platform | cache_inference_results | 3227.6889 | 0.082522 | -277.6545 | -0.0040727 | -21.04% | 25.62% | 0.95122 | TRUE | TRUE | 13.1186 | 13.1186 | 0 | 0 | 277.6545 | TRUE
i-027 | bu-platform | cache_inference_results | 17214.8672 | -0.59644 | 7733.4087 | -0.69142 | -61.12% | -35.47% | 0.02439 | TRUE | TRUE | 8592.5122 | 8592.5122 | -1.0258 | 11043.4544 | 3310.0457 | FALSE
i-030 | bu-checkout | enable_autoscaling | 24332.0343 | -1.0068 | 15441.7466 | -1.0604 | -72.96% | -55.64% | 0.02439 | TRUE | TRUE | 15905.4242 | 15905.4242 | -0.96041 | 15019.3278 | 422.4188 | FALSE
i-049 | bu-checkout | cache_inference_results | 66691.6417 | -0.83428 | 37734.9534 | -0.8851 | -66.14% | -49.7% | 0.02439 | TRUE | TRUE | 39169.6749 | 39169.6749 | -0.9021 | 39633.7904 | 1898.837 | FALSE
i-029 | bu-platform | tune_batch_size | 9034.1356 | -0.70813 | 4584.2587 | -0.65937 | -62.53% | -28.62% | 0.02439 | TRUE | TRUE | 4361.8675 | 4361.8675 | -0.78101 | 4897.0166 | 312.7579 | FALSE
i-011 | bu-datalake | consolidate_cluster | 23461.8848 | -1.2933 | 17024.9409 | -1.2686 | -80.8% | -58.81% | 0.02439 | TRUE | TRUE | 16864.08 | 16864.08 | -1.2376 | 16655.7946 | 369.1463 | FALSE
i-014 | bu-assist | migrate_storage_class | 162453.1273 | -1.2301 | 114974.3816 | -1.1727 | -79.68% | -52.85% | 0.02439 | TRUE | TRUE | 112171.3813 | 112171.3813 | -1.0059 | 103040.5327 | 11933.8489 | FALSE
i-042 | bu-search | enable_autoscaling | 17475.4415 | -0.44275 | 6251.5651 | -0.41318 | -56.93% | 1.602% | 0.12195 | FALSE | FALSE | 5914.658 | 0 | -0.72588 | 9019.0975 | 2767.5324 | FALSE
i-067 | bu-assist | consolidate_cluster | 8508.9576 | -0.62767 | 3966.5733 | -0.57325 | -62.97% | -14.2% | 0.02439 | TRUE | TRUE | 3712.5611 | 3712.5611 | -0.83058 | 4800.7669 | 834.1936 | FALSE
i-093 | bu-assist | schedule_shutdown | 769.5748 | 0.67254 | -738.1848 | 0.69503 | 30.65% | 207.3% | 0.02439 | FALSE | FALSE | -772.4701 | 0 | 0 | 0 | 738.1848 | TRUE
i-019 | bu-search | schedule_shutdown | 36036.2826 | -0.80534 | 19930.362 | -0.89976 | -66.37% | -50.83% | 0.02439 | TRUE | TRUE | 21381.5071 | 21381.5071 | -0.8692 | 20926.7787 | 996.4168 | FALSE
i-043 | bu-platform | enable_autoscaling | 21374.9756 | -0.60171 | 9664.1485 | -0.64541 | -59.11% | -32.73% | 0.02439 | TRUE | TRUE | 10164.9071 | 10164.9071 | -0.8561 | 12294.5243 | 2630.3758 | FALSE
i-034 | bu-assist | enable_autoscaling | 163805.9489 | -0.38427 | 52262.6188 | -0.36487 | -55.39% | 8.053% | 0.19512 | FALSE | FALSE | 50077.1831 | 0 | -0.77597 | 88413.3606 | 36150.7418 | FALSE
i-055 | bu-datalake | cache_inference_results | 70683.0927 | -0.78331 | 38388.7593 | -0.78999 | -66.8% | -37.95% | 0.02439 | TRUE | TRUE | 38603.603 | 38603.603 | -0.82359 | 39663.4366 | 1274.6773 | FALSE
i-036 | bu-assist | rightsize_instance | 3249.1386 | -1.2256 | 2295.2457 | -1.2088 | -76.29% | -62.42% | 0.02439 | TRUE | TRUE | 2279.1394 | 2279.1394 | -1.0937 | 2160.7671 | 134.4786 | FALSE
i-003 | bu-checkout | delete_orphaned_volume | 92502.0889 | -1.1979 | 64582.4025 | -1.2453 | -77.56% | -63.08% | 0.02439 | TRUE | TRUE | 65876.0792 | 65876.0792 | -1.2484 | 65956.0974 | 1373.695 | FALSE
i-111 | bu-checkout | rightsize_instance | 5432.7477 | -0.028725 | 153.8364 | -0.10681 | -23.82% | 6.012% | 0.2439 | FALSE | FALSE | 550.3782 | 0 | 0 | 0 | 153.8364 | TRUE
i-015 | bu-platform | enable_autoscaling | 2967.2994 | -1.0404 | 1918.8842 | -1.0227 | -72.17% | -53.53% | 0.02439 | TRUE | TRUE | 1900.1687 | 1900.1687 | -1.1358 | 2014.3335 | 95.4493 | FALSE
i-054 | bu-datalake | migrate_storage_class | 42377.0795 | -1.0295 | 27240.1885 | -1.0634 | -75.3% | -51.73% | 0.02439 | TRUE | TRUE | 27745.4039 | 27745.4039 | -0.90786 | 25282.7102 | 1957.4783 | FALSE
i-090 | bu-search | migrate_storage_class | 25476.859 | 0.17652 | -4918.6578 | 0.14463 | -8.738% | 46.33% | 0.14634 | TRUE | TRUE | -3964.6445 | -3964.6445 | 0 | 0 | 4918.6578 | TRUE
i-097 | bu-platform | delete_orphaned_volume | 7896.0818 | 0.083567 | -688.207 | 0.031886 | -25.36% | 42.8% | 0.95122 | TRUE | TRUE | -255.833 | -255.833 | 0 | 0 | 688.207 | TRUE
i-075 | bu-platform | tune_batch_size | 7165.3189 | -0.56319 | 3085.4543 | -0.59799 | -56.34% | -30.74% | 0.02439 | TRUE | TRUE | 3225.0005 | 3225.0005 | -0.58632 | 3178.7403 | 93.2859 | FALSE
i-070 | bu-search | migrate_storage_class | 15149.3389 | -0.62346 | 7027.9848 | -0.60292 | -57.33% | -29.82% | 0.02439 | TRUE | TRUE | 6859.4158 | 6859.4158 | -0.61377 | 6948.8847 | 79.1001 | FALSE
i-079 | bu-datasci | consolidate_cluster | 24354.6118 | -0.71272 | 12413.297 | -0.67857 | -62.23% | -31.86% | 0.02439 | TRUE | TRUE | 11998.517 | 11998.517 | -0.61786 | 11225.1016 | 1188.1955 | FALSE
i-005 | bu-platform | tune_batch_size | 16912.9187 | -0.8204 | 9466.9035 | -0.82625 | -67.12% | -41.74% | 0.02439 | TRUE | TRUE | 9510.3565 | 9510.3565 | -1.0557 | 11028.0211 | 1561.1176 | FALSE
i-002 | bu-checkout | tune_batch_size | 11589.5132 | -1.1336 | 7859.2541 | -1.1807 | -76.65% | -59.62% | 0.02439 | TRUE | TRUE | 8030.8986 | 8030.8986 | -1.3354 | 8540.8502 | 681.5961 | FALSE
i-026 | bu-search | enable_autoscaling | 4349.0941 | -0.77409 | 2343.6334 | -0.79943 | -66.26% | -40.09% | 0.02439 | TRUE | TRUE | 2393.805 | 2393.805 | -0.92328 | 2621.566 | 277.9326 | FALSE
i-076 | bu-datasci | rightsize_instance | 139435.0317 | -0.36768 | 42899.086 | -0.28204 | -44.78% | 3.027% | 0.073171 | TRUE | TRUE | 34267.187 | 34267.187 | -0.40393 | 46335.6046 | 3436.5186 | FALSE
i-056 | bu-search | migrate_storage_class | 7423.0138 | -0.35283 | 2206.866 | -0.42828 | -55.92% | -3.675% | 0.12195 | FALSE | FALSE | 2585.9445 | 0 | -0.65934 | 3583.8906 | 1377.0246 | FALSE
i-035 | bu-platform | consolidate_cluster | 10768.2381 | -0.96709 | 6674.304 | -0.9337 | -73.11% | -42.53% | 0.02439 | TRUE | TRUE | 6535.2646 | 6535.2646 | -1.004 | 6822.6991 | 148.3951 | FALSE
i-044 | bu-search | enable_autoscaling | 13007.0611 | -0.82505 | 7307.178 | -0.8496 | -64.59% | -48.37% | 0.02439 | TRUE | TRUE | 7445.4367 | 7445.4367 | -0.85788 | 7491.2846 | 184.1066 | FALSE
i-094 | bu-platform | tune_batch_size | 61120.3752 | 0.094824 | -6079.3842 | -0.012108 | -34.28% | 48.53% | 0.87805 | TRUE | TRUE | 735.6082 | 735.6082 | 0 | 0 | 6079.3842 | TRUE
i-080 | bu-checkout | schedule_shutdown | 9665.808 | -0.47329 | 3644.4871 | -0.55414 | -50.81% | -32.88% | 0.02439 | TRUE | TRUE | 4112.1889 | 4112.1889 | -0.47784 | 3671.8212 | 27.3341 | FALSE
i-061 | bu-platform | delete_orphaned_volume | 1131.3362 | -0.622 | 523.958 | -0.6943 | -62.6% | -33.3% | 0.02439 | TRUE | TRUE | 566.3211 | 566.3211 | -0.83046 | 638.2461 | 114.2881 | FALSE
i-018 | bu-assist | rightsize_instance | 3070.769 | -2.1311 | 2706.2487 | -2.0123 | -90.57% | -81.05% | 0.02439 | TRUE | TRUE | 2660.2718 | 2660.2718 | -1.2023 | 2147.9978 | 558.2509 | FALSE
i-012 | bu-datalake | rightsize_instance | 43215.9691 | -1.0234 | 27686.0415 | -0.90824 | -69.39% | -46.88% | 0.02439 | TRUE | TRUE | 25789.8145 | 25789.8145 | -0.96677 | 26780.4932 | 905.5483 | FALSE
i-046 | bu-assist | rightsize_instance | 43393.1482 | -0.92235 | 26140.7212 | -0.87598 | -67.06% | -47.34% | 0.02439 | TRUE | TRUE | 25321.8734 | 25321.8734 | -0.97897 | 27090.42 | 949.6988 | FALSE
i-087 | bu-checkout | migrate_storage_class | 107190.5976 | 0.38165 | -49811.2781 | 0.24126 | -5.57% | 71.57% | 0.14634 | FALSE | FALSE | -29247.0832 | 0 | 0 | 0 | 49811.2781 | TRUE
i-037 | bu-datalake | migrate_storage_class | 28532.0075 | -0.97792 | 17801.3786 | -0.98491 | -71.03% | -51.85% | 0.02439 | TRUE | TRUE | 17876.0558 | 17876.0558 | -1.0995 | 19029.4491 | 1228.0705 | FALSE
i-059 | bu-checkout | migrate_storage_class | 1365.9815 | -0.36227 | 415.1303 | -0.41638 | -48.09% | -16.23% | 0.04878 | TRUE | TRUE | 465.2123 | 465.2123 | -0.60538 | 620.3398 | 205.2095 | FALSE
i-116 | bu-platform | schedule_shutdown | 14530.6176 | 0.021145 | -310.5184 | 0.032451 | -25.94% | 44.07% | 0.78049 | TRUE | TRUE | -479.2689 | -479.2689 | 0 | 0 | 310.5184 | TRUE
i-089 | bu-platform | migrate_storage_class | 6259.4221 | 0.59424 | -5080.4581 | 0.6105 | 11.73% | 203.5% | 0.02439 | FALSE | FALSE | -5266.3819 | 0 | 0 | 0 | 5080.4581 | TRUE
i-085 | bu-datalake | migrate_storage_class | 5404.2321 | -0.2331 | 1123.6778 | -0.23497 | -39.44% | 3.216% | 0.12195 | TRUE | TRUE | 1131.6703 | 1131.6703 | -0.27641 | 1305.1239 | 181.4461 | FALSE
i-086 | bu-datasci | consolidate_cluster | 81082.081 | -0.28722 | 20242.3417 | -0.24151 | -39.49% | 1.956% | 0.14634 | TRUE | TRUE | 17396.6324 | 17396.6324 | -0.34208 | 23490.0651 | 3247.7235 | FALSE
i-001 | bu-assist | rightsize_instance | 64023.3326 | -1.1736 | 44224.8405 | -1.1311 | -76.03% | -56.56% | 0.02439 | TRUE | TRUE | 43363.9798 | 43363.9798 | -1.2176 | 45075.6283 | 850.7878 | FALSE
i-038 | bu-search | rightsize_instance | 9391.4792 | -0.66977 | 4584.6735 | -0.77633 | -64.39% | -40.55% | 0.02439 | TRUE | TRUE | 5070.5396 | 5070.5396 | -0.73966 | 4909.1603 | 324.4869 | FALSE
i-068 | bu-platform | tune_batch_size | 6615.1218 | -0.42674 | 2297.8849 | -0.48539 | -57.62% | -10.62% | 0.04878 | TRUE | TRUE | 2543.7868 | 2543.7868 | -0.54505 | 2779.6052 | 481.7203 | FALSE
i-102 | bu-assist | rightsize_instance | 21771.2061 | 0.33353 | -8618.9409 | 0.32907 | -4.551% | 102.3% | 0.12195 | TRUE | TRUE | -8483.8077 | -8483.8077 | 0 | 0 | 8618.9409 | TRUE
i-000 | bu-assist | rightsize_instance | 13571.0434 | -1.0221 | 8687.7236 | -0.97375 | -76.82% | -38.48% | 0.02439 | TRUE | TRUE | 8445.7716 | 8445.7716 | -1.2388 | 9639.1207 | 951.3971 | FALSE
i-041 | bu-platform | migrate_storage_class | 19871.2887 | -0.79387 | 10887.6171 | -0.89791 | -71.28% | -42.2% | 0.02439 | TRUE | TRUE | 11775.3315 | 11775.3315 | -0.77328 | 10700.7688 | 186.8483 | FALSE
i-110 | bu-platform | schedule_shutdown | 14453.3067 | 0.29641 | -4986.609 | 0.16749 | -28.18% | 94.64% | 0.63415 | TRUE | TRUE | -2635.3085 | -2635.3085 | 0 | 0 | 4986.609 | TRUE
i-109 | bu-platform | delete_orphaned_volume | 7578.699 | 0.19581 | -1639.1952 | 0.090869 | -14.66% | 40.53% | 0.39024 | FALSE | FALSE | -720.9304 | 0 | 0 | 0 | 1639.1952 | TRUE
i-051 | bu-checkout | delete_orphaned_volume | 3338.5637 | -0.73017 | 1729.9527 | -0.90407 | -69.85% | -45.63% | 0.02439 | TRUE | TRUE | 1986.7152 | 1986.7152 | -0.92363 | 2012.905 | 282.9523 | FALSE
i-058 | bu-platform | cache_inference_results | 8167.5298 | -0.3928 | 2653.1094 | -0.46053 | -57% | -7.421% | 0.04878 | TRUE | TRUE | 3014.2419 | 3014.2419 | -0.7129 | 4163.6248 | 1510.5154 | FALSE
i-057 | bu-checkout | schedule_shutdown | 68304.092 | -0.41481 | 23191.5802 | -0.64769 | -61% | -29.8% | 0.04878 | TRUE | TRUE | 32563.6708 | 32563.6708 | -0.70996 | 34721.3123 | 11529.7321 | FALSE
i-081 | bu-assist | enable_autoscaling | 1199.351 | -0.3698 | 370.7546 | -0.26895 | -52.25% | 22.31% | 0.14634 | TRUE | TRUE | 282.8291 | 282.8291 | -0.44231 | 428.7041 | 57.9495 | FALSE
i-004 | bu-search | rightsize_instance | 2078.1554 | -0.90497 | 1237.4328 | -1.0776 | -73.83% | -55.72% | 0.02439 | TRUE | TRUE | 1370.7262 | 1370.7262 | -1.1942 | 1448.5963 | 211.1635 | FALSE
i-092 | bu-search | delete_orphaned_volume | 1239.7233 | 0.54996 | -908.9511 | 0.32062 | -3.736% | 97.25% | 0.12195 | FALSE | FALSE | -468.5963 | 0 | 0 | 0 | 908.9511 | TRUE
i-100 | bu-checkout | delete_orphaned_volume | 16317.347 | 0.36471 | -7181.2941 | 0.1635 | -9.554% | 53.33% | 0.17073 | TRUE | TRUE | -2898.385 | -2898.385 | 0 | 0 | 7181.2941 | TRUE
i-113 | bu-platform | cache_inference_results | 3686.2502 | 0.10907 | -424.7862 | 0.070392 | -25.35% | 54.2% | 0.78049 | TRUE | TRUE | -268.8317 | -268.8317 | 0 | 0 | 424.7862 | TRUE
i-017 | bu-checkout | cache_inference_results | 5788.1073 | -1.0319 | 3725.6755 | -1.1332 | -73.51% | -60.85% | 0.02439 | TRUE | TRUE | 3924.3113 | 3924.3113 | -0.98715 | 3631.2338 | 94.4417 | FALSE
i-112 | bu-checkout | consolidate_cluster | 15554.5516 | 0.30803 | -5611.1673 | 0.15681 | -11.35% | 54.35% | 0.17073 | TRUE | TRUE | -2640.6837 | -2640.6837 | 0 | 0 | 5611.1673 | TRUE
i-048 | bu-search | delete_orphaned_volume | 8066.005 | -0.8661 | 4673.5408 | -0.93301 | -66.76% | -53.44% | 0.02439 | TRUE | TRUE | 4893.0931 | 4893.0931 | -0.867 | 4676.5821 | 3.0413 | FALSE
i-077 | bu-search | enable_autoscaling | 67126.3948 | -0.25618 | 15170.6396 | -0.3318 | -40.44% | -13.53% | 0.02439 | TRUE | TRUE | 18954.3325 | 18954.3325 | -0.38961 | 21660.4192 | 6489.7795 | FALSE
i-047 | bu-platform | schedule_shutdown | 45890.8969 | -0.60088 | 20727.7068 | -0.63762 | -54.78% | -38.22% | 0.02439 | TRUE | TRUE | 21635.3474 | 21635.3474 | -0.80854 | 25446.1392 | 4718.4323 | FALSE
i-033 | bu-datalake | cache_inference_results | 8261.4494 | -1.076 | 5444.6205 | -1.0522 | -72.78% | -55.22% | 0.02439 | TRUE | TRUE | 5376.8992 | 5376.8992 | -1.0653 | 5414.2147 | 30.4058 | FALSE
i-082 | bu-platform | rightsize_instance | 5802.3592 | -0.43509 | 2047.0353 | -0.41812 | -55.26% | -3.135% | 0.073171 | TRUE | TRUE | 1982.7486 | 1982.7486 | -0.35027 | 1714.5914 | 332.4439 | FALSE
i-078 | bu-datasci | delete_orphaned_volume | 8290.8592 | -0.38442 | 2646.0509 | -0.42246 | -47.89% | -17.56% | 0.04878 | TRUE | TRUE | 2856.781 | 2856.781 | -0.39634 | 2712.9748 | 66.9239 | FALSE
i-106 | bu-checkout | cache_inference_results | 10031.0281 | 0.10107 | -1066.8127 | 0.13267 | -8.22% | 42.07% | 0.34146 | TRUE | TRUE | -1423.1492 | -1423.1492 | 0 | 0 | 1066.8127 | TRUE
i-096 | bu-assist | cache_inference_results | 7432.6589 | -0.01222 | 90.2768 | -0.097624 | -31.44% | 19.99% | 0.53659 | FALSE | FALSE | 691.3102 | 0 | 0 | 0 | 90.2768 | TRUE
i-098 | bu-checkout | cache_inference_results | 1818.1866 | -0.098906 | 171.2228 | 0.0308 | -13.64% | 23.16% | 0.70732 | TRUE | TRUE | -56.8708 | -56.8708 | 0 | 0 | 171.2228 | TRUE
i-009 | bu-search | rightsize_instance | 35564.8197 | -1.2931 | 25805.5662 | -1.1112 | -73.55% | -59.04% | 0.02439 | TRUE | TRUE | 23858.6126 | 23858.6126 | -1.2729 | 25605.9652 | 199.601 | FALSE
i-064 | bu-checkout | consolidate_cluster | 7939.9168 | -1.1666 | 5467.2108 | -0.95702 | -69.34% | -51.89% | 0.02439 | TRUE | TRUE | 4890.721 | 4890.721 | -0.89971 | 4710.8403 | 756.3705 | FALSE
i-031 | bu-checkout | consolidate_cluster | 4699.2734 | -1.1906 | 3270.564 | -0.95582 | -67.89% | -53.96% | 0.02439 | TRUE | TRUE | 2892.4093 | 2892.4093 | -0.98465 | 2943.7739 | 326.7901 | FALSE
i-074 | bu-search | enable_autoscaling | 30223.0037 | -0.92254 | 18209.0777 | -0.71103 | -58.97% | -41.21% | 0.02439 | TRUE | TRUE | 15379.2984 | 15379.2984 | -0.67391 | 14818.0111 | 3391.0666 | FALSE
i-010 | bu-platform | tune_batch_size | 147563.5106 | -1.3325 | 108633.0968 | -1.2561 | -80.1% | -59.26% | 0.02439 | TRUE | TRUE | 105543.7632 | 105543.7632 | -1.0745 | 97173.3972 | 11459.6996 | FALSE
i-022 | bu-assist | cache_inference_results | 183203.3151 | -1.1002 | 122235.3311 | -1.1661 | -74.86% | -61.39% | 0.02439 | TRUE | TRUE | 126121.4039 | 126121.4039 | -1.1419 | 124725.2065 | 2489.8754 | FALSE
i-104 | bu-checkout | consolidate_cluster | 35723.1327 | 0.052573 | -1928.2991 | 0.30278 | 7.899% | 69.82% | 0.04878 | FALSE | FALSE | -12632.4603 | 0 | 0 | 0 | 1928.2991 | TRUE
i-040 | bu-datasci | enable_autoscaling | 134432.9011 | -0.71088 | 68398.2098 | -0.8139 | -63.33% | -46.45% | 0.02439 | TRUE | TRUE | 74862.2489 | 74862.2489 | -0.83029 | 75830.6871 | 7432.4773 | FALSE
i-050 | bu-datalake | cache_inference_results | 112472.5286 | -0.83909 | 63872.6645 | -0.90146 | -67.02% | -50.02% | 0.02439 | TRUE | TRUE | 66811.2798 | 66811.2798 | -0.99741 | 70988.7902 | 7116.1257 | FALSE
i-052 | bu-search | cache_inference_results | 13985.0041 | -1.0401 | 9042.4961 | -0.81148 | -63.64% | -45.73% | 0.02439 | TRUE | TRUE | 7772.8374 | 7772.8374 | -0.84813 | 7996.3938 | 1046.1023 | FALSE
i-039 | bu-platform | schedule_shutdown | 52124.8647 | -0.8077 | 28883.3428 | -0.8964 | -69.23% | -45.9% | 0.02439 | TRUE | TRUE | 30856.0351 | 30856.0351 | -0.88611 | 30636.1274 | 1752.7846 | FALSE
i-091 | bu-platform | migrate_storage_class | 480.3286 | 0.27773 | -153.7649 | 0.21992 | -25.65% | 108.8% | 0.39024 | TRUE | TRUE | -118.1484 | -118.1484 | 0 | 0 | 153.7649 | TRUE
i-063 | bu-datasci | tune_batch_size | 1530.3876 | -0.64073 | 724.0143 | -0.7348 | -62.75% | -38.25% | 0.02439 | TRUE | TRUE | 796.4136 | 796.4136 | -0.60876 | 697.8172 | 26.1971 | FALSE
i-072 | bu-platform | cache_inference_results | 18055.1267 | -0.87453 | 10525.1266 | -0.96599 | -71.35% | -49.44% | 0.02439 | TRUE | TRUE | 11183.2478 | 11183.2478 | -0.74131 | 9452.0512 | 1073.0755 | FALSE
i-020 | bu-checkout | delete_orphaned_volume | 90455.3813 | -1.166 | 62267.4585 | -1.04 | -71.41% | -56.31% | 0.02439 | TRUE | TRUE | 58484.8736 | 58484.8736 | -1.0934 | 60146.5042 | 2120.9544 | FALSE
i-032 | bu-datalake | cache_inference_results | 15192.2543 | -1.0158 | 9691.1851 | -1.1375 | -76.6% | -56.08% | 0.02439 | TRUE | TRUE | 10321.5367 | 10321.5367 | -1.1067 | 10168.7536 | 477.5686 | FALSE
i-103 | bu-assist | consolidate_cluster | 39578.2949 | 0.60923 | -33206.6241 | 0.44148 | 7.568% | 124.8% | 0.073171 | FALSE | FALSE | -21966.1004 | 0 | 0 | 0 | 33206.6241 | TRUE
i-025 | bu-checkout | schedule_shutdown | 69145.0406 | -1.0532 | 45025.0718 | -0.94253 | -69.62% | -50.02% | 0.02439 | TRUE | TRUE | 42203.2291 | 42203.2291 | -0.9453 | 42277.8256 | 2747.2463 | FALSE
i-006 | bu-assist | migrate_storage_class | 360421.4951 | -1.3601 | 267923.7442 | -1.4474 | -80.95% | -70.96% | 0.02439 | TRUE | TRUE | 275657.0707 | 275657.0707 | -1.23 | 255077.6965 | 12846.0477 | FALSE
i-007 | bu-datasci | cache_inference_results | 22136.4863 | -1.0638 | 14496.2629 | -1.1842 | -76.7% | -59.82% | 0.02439 | TRUE | TRUE | 15363.0353 | 15363.0353 | -1.2057 | 15506.8853 | 1010.6225 | FALSE
i-024 | bu-datalake | delete_orphaned_volume | 62329.6698 | -0.64048 | 29479.4624 | -0.79612 | -65.59% | -40.88% | 0.02439 | TRUE | TRUE | 34214.267 | 34214.267 | -0.94341 | 38064.8151 | 8585.3527 | FALSE
i-107 | bu-platform | enable_autoscaling | 2242.9771 | 0.12123 | -289.0876 | 0.065695 | -16.7% | 36.9% | 0.53659 | TRUE | TRUE | -152.3002 | -152.3002 | 0 | 0 | 289.0876 | TRUE
i-095 | bu-assist | consolidate_cluster | 42519.1642 | 0.91551 | -63696.3025 | 0.77353 | 41.04% | 233.1% | 0.02439 | FALSE | FALSE | -49637.2179 | 0 | 0 | 0 | 63696.3025 | TRUE
i-073 | bu-search | consolidate_cluster | 12133.1675 | -0.30571 | 3195.9163 | -0.30603 | -41.04% | -8.039% | 0.04878 | TRUE | TRUE | 3198.7045 | 3198.7045 | -0.40803 | 4065.0901 | 869.1739 | FALSE
i-069 | bu-checkout | migrate_storage_class | 14480.7663 | -0.4415 | 5168.5896 | -0.48556 | -51.51% | -21.9% | 0.02439 | TRUE | TRUE | 5569.9657 | 5569.9657 | -0.6316 | 6780.7562 | 1612.1666 | FALSE
i-008 | bu-checkout | migrate_storage_class | 21594.4698 | -1.1626 | 14842.5387 | -1.152 | -74.96% | -60.11% | 0.02439 | TRUE | TRUE | 14770.4218 | 14770.4218 | -1.0583 | 14099.956 | 742.5827 | FALSE
i-060 | bu-assist | tune_batch_size | 28765.0369 | -0.73248 | 14937.2467 | -0.88153 | -71.84% | -39.09% | 0.02439 | TRUE | TRUE | 16852.0915 | 16852.0915 | -0.90455 | 17123.1189 | 2185.8721 | FALSE
i-105 | bu-platform | cache_inference_results | 20189.8315 | 0.058797 | -1222.6962 | 0.034574 | -26.63% | 46.05% | 0.90244 | TRUE | TRUE | -710.2432 | -710.2432 | 0 | 0 | 1222.6962 | TRUE
i-101 | bu-assist | delete_orphaned_volume | 108357.5909 | 0.18512 | -22035.8655 | 0.072649 | -15.36% | 36.63% | 0.60976 | TRUE | TRUE | -8165.1032 | -8165.1032 | 0 | 0 | 22035.8655 | TRUE
i-115 | bu-assist | delete_orphaned_volume | 14576.2623 | 0.30714 | -5240.6417 | 0.11476 | -22.87% | 63.09% | 0.36585 | TRUE | TRUE | -1772.4692 | -1772.4692 | 0 | 0 | 5240.6417 | TRUE
i-062 | bu-assist | schedule_shutdown | 30824.3679 | -0.86903 | 17897.968 | -0.9765 | -70.08% | -52.59% | 0.02439 | TRUE | TRUE | 19215.1224 | 19215.1224 | -0.9058 | 18364.6282 | 466.6601 | FALSE
i-083 | bu-search | schedule_shutdown | 44072.1077 | -0.43775 | 15624.2409 | -0.52431 | -52.57% | -26.11% | 0.02439 | TRUE | TRUE | 17983.1334 | 17983.1334 | -0.58253 | 19458.4885 | 3834.2476 | FALSE
i-066 | bu-search | tune_batch_size | 43845.373 | -0.54629 | 18454.8286 | -0.61124 | -58.7% | -28.69% | 0.02439 | TRUE | TRUE | 20051.5205 | 20051.5205 | -0.55083 | 18569.7416 | 114.913 | FALSE
i-099 | bu-platform | enable_autoscaling | 14765.1469 | 0.32712 | -5713.7376 | 0.2286 | -6.396% | 68.76% | 0.14634 | TRUE | TRUE | -3792.2635 | -3792.2635 | 0 | 0 | 5713.7376 | TRUE
i-065 | bu-datasci | migrate_storage_class | 5199.6114 | -0.83811 | 2950.6476 | -0.90087 | -67.23% | -49.65% | 0.02439 | TRUE | TRUE | 3087.4397 | 3087.4397 | -0.79851 | 2859.7849 | 90.8627 | FALSE
i-021 | bu-platform | cache_inference_results | 64151.6059 | -0.75885 | 34115.6363 | -0.82728 | -66.07% | -43.65% | 0.02439 | TRUE | TRUE | 36102.2699 | 36102.2699 | -1.0318 | 41290.8763 | 7175.24 | FALSE
i-045 | bu-checkout | delete_orphaned_volume | 14615.7873 | -0.89623 | 8651.0128 | -0.95921 | -68.12% | -53.94% | 0.02439 | TRUE | TRUE | 9015.1038 | 9015.1038 | -0.74012 | 7643.2026 | 1007.8102 | FALSE
i-013 | bu-search | rightsize_instance | 19555.668 | -0.84011 | 11114.2009 | -0.92778 | -66.99% | -52.63% | 0.02439 | TRUE | TRUE | 11822.7823 | 11822.7823 | -1.0919 | 12993.2367 | 1879.0358 | FALSE
i-053 | bu-search | cache_inference_results | 72551.0286 | -0.68277 | 35897.1503 | -0.75705 | -60.28% | -44.61% | 0.02439 | TRUE | TRUE | 38521.0132 | 38521.0132 | -0.66448 | 35220.7244 | 676.4259 | FALSE
i-023 | bu-assist | consolidate_cluster | 87962.8729 | -0.66296 | 42633.6713 | -0.74511 | -60.67% | -42.71% | 0.02439 | TRUE | TRUE | 46208.5717 | 46208.5717 | -0.91157 | 52611.3533 | 9977.6821 | FALSE
i-016 | bu-checkout | consolidate_cluster | 14046.9472 | -0.87191 | 8173.2116 | -0.91293 | -65.8% | -52.9% | 0.02439 | TRUE | TRUE | 8409.2814 | 8409.2814 | -1.0051 | 8905.8955 | 732.6839 | FALSE
i-071 | bu-datalake | migrate_storage_class | 7974.8072 | -0.57133 | 3470.8228 | -0.68028 | -65.43% | -25.81% | 0.02439 | TRUE | TRUE | 3935.7692 | 3935.7692 | -0.54055 | 3330.0555 | 140.7672 | FALSE
i-084 | bu-search | delete_orphaned_volume | 25217.666 | -0.43688 | 8925.8736 | -0.53734 | -51.5% | -29.6% | 0.02439 | TRUE | TRUE | 10483.0418 | 10483.0418 | -0.59648 | 11329.0877 | 2403.2141 | FALSE
i-108 | bu-search | schedule_shutdown | 17874.353 | 0.20431 | -4051.8178 | 0.11883 | -7.462% | 37.06% | 0.2439 | FALSE | FALSE | -2255.3727 | 0 | 0 | 0 | 4051.8178 | TRUE
Total |  |  | 4124601.8218 |  | 1693741.0017 |  |  |  |  | 103 | 103 | 1809486.9023 | 1872634.0413 |  | 2020441.1259 | 450967.8445 | 30
Summary
Events measured |  |  | 117
Passing parallel trends |  |  | 103
Credited under current policy |  |  | 103
SIMULATED: events with zero true effect |  |  | 30
Before/after would report (annual) |  |  | 1693741.0017
Identified estimate, all events (annual) |  |  | 1809486.9023
Credited savings (annual) |  |  | 1872634.0413
SIMULATED: true savings (annual) |  |  | 2020441.1259
SIMULATED: gross misattribution of before/after |  |  | 450967.8445
SIMULATED: before/after credited to zero-effect events |  |  | -231036.2584
SIMULATED: identified estimate on zero-effect events |  |  | -150778.8755
SIMULATED: credited to zero-effect events (after gate) |  |  | -29053.9509
SIMULATED: before/after error as share of true savings |  |  | 22.32%
Annual $ = −(e^effect − 1) × annualised run-rate. A log effect of −0.10 is a 9.5% cost reduction; the conversion is exact, not approximate.

## 05 Budget vs Actual
Budget vs actual
Budget = average of the first six complete months, grown monthly at the budget growth assumption. Actuals link to Raw Cost Data. Cost variance: under budget is favourable.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Monthly growth factor | 1.0117 | (1 + annual budget growth)^(1/12)
Baseline (avg. months 1–6) | 157209.3672 |  |  | 86225.5614 |  |  | 63959.1058 |  |  | 150202.6796 |  |  | 71068.8183 |  |  | 86269.1863 |  |  | 74231.5702
Month | bu-assist budget | bu-assist actual | bu-assist var | bu-checkout budget | bu-checkout actual | bu-checkout var | bu-datalake budget | bu-datalake actual | bu-datalake var | bu-datasci budget | bu-datasci actual | bu-datasci var | bu-platform budget | bu-platform actual | bu-platform var | bu-search budget | bu-search actual | bu-search var | unallocated budget | unallocated actual | unallocated var | Total budget | Total actual | Total variance | Variance % | Status
2025-07-01 | 159051.0619 | 157484.6965 | -1566.3654 | 87235.6867 | 93742.4528 | 6506.7661 | 64708.3814 | 71220.4689 | 6512.0875 | 151962.2915 | 154568.5751 | 2606.2836 | 71901.3836 | 70392.8494 | -1508.5341 | 87279.8226 | 97421.9546 | 10142.132 | 75101.1869 | 78358.7276 | 3257.5407 | 697239.8145 | 723189.7249 | 25949.9104 | 3.722% | On plan
2025-08-01 | 160914.3319 | 164579.1068 | 3664.775 | 88257.6455 | 97362.1618 | 9104.5163 | 65466.4347 | 63816.123 | -1650.3117 | 153742.5171 | 143516.3148 | -10226.2023 | 72743.7023 | 73737.5983 | 993.8961 | 88302.2985 | 100098.4352 | 11796.1368 | 75980.9911 | 77229.2808 | 1248.2897 | 705407.9209 | 720339.0207 | 14931.0998 | 2.117% | On plan
2025-09-01 | 162799.4299 | 158979.4144 | -3820.0155 | 89291.5765 | 92261.5062 | 2969.9297 | 66233.3685 | 61211.5172 | -5021.8513 | 155543.5979 | 159667.5958 | 4123.9979 | 73595.8887 | 77160.9571 | 3565.0684 | 89336.7526 | 95928.8624 | 6592.1099 | 76871.1021 | 81095.158 | 4224.056 | 713671.7161 | 726305.0112 | 12633.2951 | 1.77% | On plan
2025-10-01 | 164706.6117 | 173558.5418 | 8851.9301 | 90337.6199 | 111068.9696 | 20731.3497 | 67009.2869 | 61411.7857 | -5597.5012 | 157365.7783 | 164202.5117 | 6836.7334 | 74458.0584 | 87267.349 | 12809.2905 | 90383.3252 | 109009.5874 | 18626.2622 | 77771.6406 | 85190.819 | 7419.1784 | 722032.321 | 791709.5642 | 69677.2432 | 9.65% | Unfavourable
2025-11-01 | 166636.136 | 170043.1224 | 3406.9864 | 91395.9176 | 132965.7974 | 41569.8798 | 67794.2952 | 58841.3899 | -8952.9053 | 159209.3053 | 144469.2641 | -14740.0412 | 75330.3284 | 85378.4664 | 10048.138 | 91442.1583 | 119213.6236 | 27771.4652 | 78682.7289 | 90806.4504 | 12123.7215 | 730490.8697 | 801718.1142 | 71227.2446 | 9.751% | Unfavourable
2025-12-01 | 168588.2644 | 196719.2147 | 28130.9502 | 92466.6132 | 126834.2342 | 34367.6211 | 68588.4997 | 67374.5645 | -1213.9352 | 161074.4291 | 179764.6248 | 18690.1957 | 76212.8169 | 77821.1707 | 1608.3538 | 92513.3956 | 113922.0861 | 21408.6905 | 79604.4906 | 93942.017 | 14337.5264 | 739048.5095 | 856377.9119 | 117329.4024 | 15.88% | Unfavourable
2026-01-01 | 170563.262 | 198025.435 | 27462.173 | 93549.8518 | 102962.322 | 9412.4702 | 69392.0083 | 68852.6929 | -539.3153 | 162961.4026 | 181287.5053 | 18326.1027 | 77105.6438 | 78034.4955 | 928.8517 | 93597.1824 | 92404.9375 | -1192.2449 | 80537.0506 | 83037.662 | 2500.6114 | 747706.4014 | 804605.0502 | 56898.6488 | 7.61% | Unfavourable
2026-02-01 | 172561.3964 | 172349.5835 | -211.8129 | 94645.7806 | 93784.6565 | -861.1241 | 70204.9299 | 64577.3672 | -5627.5627 | 164870.4819 | 145215.4029 | -19655.079 | 78008.93 | 67682.0376 | -10326.8923 | 94693.6656 | 87466.7319 | -7226.9337 | 81480.5354 | 77358.6495 | -4121.8859 | 756465.7198 | 708434.4292 | -48031.2906 | -6.349% | Favourable
2026-03-01 | 174582.9388 | 207714.8918 | 33131.953 | 95754.548 | 107075.4452 | 11320.8971 | 71027.3748 | 74857.5749 | 3830.2 | 166801.9259 | 219042.9453 | 52241.0194 | 78922.7981 | 74464.0145 | -4458.7836 | 95802.994 | 100600.7407 | 4797.7467 | 82435.0731 | 86338.6019 | 3903.5288 | 765327.6528 | 870094.2144 | 104766.5615 | 13.69% | Unfavourable
2026-04-01 | 176628.1634 | 215101.3348 | 38473.1714 | 96876.3046 | 99504.5953 | 2628.2907 | 71859.4546 | 78120.4239 | 6260.9693 | 168755.9966 | 239549.4396 | 70793.443 | 79847.3721 | 72718.1095 | -7129.2626 | 96925.3181 | 94561.9203 | -2363.3978 | 83400.7932 | 81252.9156 | -2147.8776 | 774293.4027 | 880808.739 | 106515.3364 | 13.76% | Unfavourable
2026-05-01 | 178697.3477 | 199289.5748 | 20592.2271 | 98011.2025 | 107902.8159 | 9891.6134 | 72701.2821 | 79901.8988 | 7200.6167 | 170732.9591 | 182830.5607 | 12097.6016 | 80782.7775 | 77319.3466 | -3463.4308 | 98060.7902 | 102550.6498 | 4489.8596 | 84377.8265 | 87225.1647 | 2847.3382 | 783364.1856 | 837020.0112 | 53655.8256 | 6.849% | Unfavourable
Total | 1855728.944 | 2013844.9165 | 158115.9724 | 1017822.7468 | 1165464.9569 | 147642.2101 | 754985.3161 | 750185.8069 | -4799.5092 | 1773020.6852 | 1914114.7401 | 141094.0549 | 838909.6998 | 841976.3948 | 3066.695 | 1018337.7031 | 1113179.5295 | 94841.8264 | 876243.419 | 921835.4465 | 45592.0275 | 8135048.514 | 8720601.7911 | 585553.2772 | 7.198%
Every business unit's bill rose over the period. Budget vs actual cannot tell you whether that is growth or waste -- the unit-economics layer in the repository does. This sheet shows the variance; the engine explains it.

## 06 Forecast
Forecast
Twelve months forward. Trend = linear regression of each unit's monthly actuals on time (FORECAST). Run-rate = last three months' average grown at the active scenario's cloud growth. Two methods shown so the gap between them is visible.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Monthly growth factor (active scenario) | 1.0117
Last 3 months avg. total | 862640.9882
Month | bu-assist (trend) | bu-checkout (trend) | bu-datalake (trend) | bu-datasci (trend) | bu-platform (trend) | bu-search (trend) | unallocated (trend) | Total (trend) | Total (run-rate × growth) | Gap
2026-06-01 | 207745.8453 | 116352.8577 | 74573.1724 | 200417.0633 | 78415.8995 | 106842.6781 | 89642.2786 | 873989.7949 | 872746.7557 | -1243.0392
2026-07-01 | 211501.2587 | 118282.1404 | 75447.705 | 204284.7709 | 78838.651 | 108055.2983 | 90666.4215 | 887076.2458 | 882970.9115 | -4105.3344
2026-08-01 | 215256.6721 | 120211.4231 | 76322.2377 | 208152.4784 | 79261.4026 | 109267.9184 | 91690.5645 | 900162.6968 | 893314.8423 | -6847.8544
2026-09-01 | 219012.0855 | 122140.7058 | 77196.7703 | 212020.186 | 79684.1541 | 110480.5386 | 92714.7074 | 913249.1477 | 903779.9515 | -9469.1962
2026-10-01 | 222767.4989 | 124069.9885 | 78071.3029 | 215887.8936 | 80106.9057 | 111693.1587 | 93738.8503 | 926335.5986 | 914367.6585 | -11967.9401
2026-11-01 | 226522.9123 | 125999.2712 | 78945.8355 | 219755.6012 | 80529.6572 | 112905.7789 | 94762.9933 | 939422.0495 | 925079.3997 | -14342.6498
2026-12-01 | 230278.3257 | 127928.5539 | 79820.3681 | 223623.3087 | 80952.4088 | 114118.399 | 95787.1362 | 952508.5004 | 935916.628 | -16591.8724
2027-01-01 | 234033.7391 | 129857.8366 | 80694.9007 | 227491.0163 | 81375.1603 | 115331.0191 | 96811.2791 | 965594.9514 | 946880.8135 | -18714.1378
2027-02-01 | 237789.1525 | 131787.1194 | 81569.4333 | 231358.7239 | 81797.9119 | 116543.6393 | 97835.4221 | 978681.4023 | 957973.4436 | -20707.9587
2027-03-01 | 241544.5659 | 133716.4021 | 82443.966 | 235226.4314 | 82220.6634 | 117756.2594 | 98859.565 | 991767.8532 | 969196.0229 | -22571.8303
2027-04-01 | 245299.9793 | 135645.6848 | 83318.4986 | 239094.139 | 82643.415 | 118968.8796 | 99883.7079 | 1004854.3041 | 980550.0738 | -24304.2303
2027-05-01 | 249055.3927 | 137574.9675 | 84193.0312 | 242961.8466 | 83066.1665 | 120181.4997 | 100907.8509 | 1017940.755 | 992037.1364 | -25903.6186
12-month total | 2740807.428 | 1523566.9509 | 952597.2216 | 2660273.4593 | 968892.3959 | 1362145.0671 | 1143300.7769 | 11351583.2998 | 11174813.6374 | -176769.6623
A linear trend extrapolates the whole history; the run-rate method trusts only the last quarter. When they disagree by more than ~10%, the recent quarter contains something the trend has not caught up with.

## 07 ROI Analysis
ROI analysis
Programme economics under the active scenario. Savings are the credited annual figure from Savings Attribution, scaled by effect realisation and decayed by persistence. Costs are the programme inputs scaled by the cost multiplier.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Inputs (links)
Credited annual savings (measurement) | 1872634.0413
Effect realisation (scenario) | 100%
Savings persistence (scenario) | 85%
Programme cost multiplier (scenario) | 1
Discount rate | 12%
Annual programme run cost | 330000
One-time setup (year 0) | 50000
Intervention engineering, one-time (year 0) | 280800
Year-1 ramp | 50%
Cash flows
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Note
Realised savings | 0 | 936317.0206 | 1591738.9351 | 1352978.0948 | 1150031.3806 | 977526.6735 | credited × realisation × ramp (yr 1) or persistence^(t−1) (yr 2+)
Programme cost | -330800 | -330000 | -330000 | -330000 | -330000 | -330000 | setup + intervention engineering in year 0; run cost yrs 1–5; × cost multiplier
Net cash flow | -330800 | 606317.0206 | 1261738.9351 | 1022978.0948 | 820031.3806 | 647526.6735
Cumulative net cash flow | -330800 | 275517.0206 | 1537255.9557 | 2560234.0506 | 3380265.4312 | 4027792.1047
Discount factor | 1 | 0.89286 | 0.79719 | 0.71178 | 0.63552 | 0.56743
Present value of net | -330800 | 541354.4827 | 1005850.5541 | 728135.6019 | 521144.7672 | 367424.0243
Results
Net present value (5 years) | Year 0: 2833109.4303
Present value of savings | Year 0: 4353485.5771
Present value of programme cost | Year 0: 1520376.1468
Benefit-to-cost ratio | Year 0: 2.8634
Return on investment (PV basis) | Year 0: 186.3%
Internal rate of return | Year 0: 233.6%
Payback (months) | Year 0: 6.5471
Year-1 ROI (net year 1 ÷ year-0 outlay + run) | Year 0: 190.9%
What the before/after number would have said
Before/after reported annual savings | Year 0: 1693741.0017
Credited savings (identified, gated) | Year 0: 1872634.0413
Difference the method makes to the headline | Year 0: 178893.0396
SIMULATED: gross misattribution inside the before/after total | Year 0: 450967.8445
The aggregate can look close while every individual attribution is wrong: errors in both directions net out. Gross misattribution is the sum of the absolute errors, and it is what a budget owner actually experiences.

## 08 Scenario Analysis
Scenario analysis
Base, Bull and Bear computed side by side from the driver table on Assumptions. Independent of the active-scenario selector, so all three are always visible.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
| Base | Bull | Bear | How it is computed
Drivers
Effect realisation | 100% | 110% | 75%
Programme cost multiplier | 1 | 0.9 | 1.3
Cloud growth (forecast) | 15% | 10% | 25%
Savings persistence | 85% | 90% | 70%
Constants
Credited annual savings | 1872634.0413 | 1872634.0413 | 1872634.0413
Discount rate | 12% | 12% | 12%
Annual run cost (before multiplier) | 330000 | 330000 | 330000
Setup (before multiplier) | 50000 | 50000 | 50000
Intervention engineering (before multiplier) | 280800 | 280800 | 280800
Year-1 ramp | 50% | 50% | 50%
Results
Year-1 realised savings | 936317.0206 | 1029948.7227 | 702237.7655 | credited × realisation × ramp
PV of savings, 5 years | 4353485.5771 | 5306350.4091 | 2398083.6779 | credited·real·[ramp/(1+r) + Σ₂₋₅ persist^(t−1)/(1+r)^t]
PV of programme cost | 1520376.1468 | 1368338.5321 | 1976488.9908 | (setup + engineering)·mult + Σ run·mult / (1+r)^t
NPV | 2833109.4303 | 3938011.877 | 421594.6871 | PV savings − PV cost
ROI (PV basis) | 186.3% | 287.8% | 21.33% | (PV savings − PV cost) / PV cost
Benefit-to-cost ratio | 2.8634 | 3.878 | 1.2133 | PV savings / PV cost
Simple payback (months) | 6.5471 | 4.8743 | 18.8864 | 12 × year-0 outlay / (year-1 savings − run cost), if within year 1
Bear is not a stress test of the measurement -- the estimator's error is on the Savings Attribution sheet. Bear is a stress test of execution: what if a quarter of measured savings never reach production, hiring runs 30% over, and savings decay faster.

## 09 Sensitivity Analysis
Sensitivity analysis
Five-year NPV as two inputs move together, everything else at the active scenario. Each cell is the full NPV formula, so the grid recalculates.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
NPV: effect realisation (rows) × programme cost multiplier (columns)
realisation ↓ / cost × → | 0.8 | 1 | 1.2 | 1.5 | 2
50% | 960441.8711 | 656366.6418 | 352291.4124 | -103821.4316 | -864009.505
62.5% | 1504627.5682 | 1200552.3389 | 896477.1095 | 440364.2655 | -319823.8079
75% | 2048813.2654 | 1744738.036 | 1440662.8067 | 984549.9626 | 224361.8892
87.5% | 2592998.9625 | 2288923.7332 | 1984848.5038 | 1528735.6598 | 768547.5864
100% | 3137184.6596 | 2833109.4303 | 2529034.2009 | 2072921.3569 | 1312733.2835
112.5% | 3681370.3568 | 3377295.1274 | 3073219.8981 | 2617107.054 | 1856918.9806
125% | 4225556.0539 | 3921480.8246 | 3617405.5952 | 3161292.7512 | 2401104.6778
NPV: discount rate (rows) × savings persistence (columns)
rate ↓ / persistence → | 60% | 70% | 80% | 85% | 90% | 100%
8% | 1179500.1143 | 1848939.2712 | 2681114.6469 | 3167858.731 | 3707225.5918 | 4961530.2159
10% | 1131478.9698 | 1760066.1644 | 2539114.2967 | 2993890.9113 | 3497227.2237 | 4665799.4223
12% | 1085948.8195 | 1677068.7571 | 2407523.0581 | 2833109.4303 | 3303578.7706 | 4394053.1411
15% | 1021958.5447 | 1562479.695 | 2227526.1183 | 2613903.6011 | 3040280.4637 | 4026159.8523
20% | 925557.5225 | 1394333.1399 | 1967113.879 | 2298362.1016 | 2662864.4944 | 3502355.9075
Check: grid 1 at (100%, 1.00x) − ROI NPV, Base scenario | 0

## 10 Assumptions
Assumptions
Blue cells are inputs. Everything else in the workbook is a formula that reads them. Change one here and every sheet moves.
Financial
Discount rate (cost of capital) | 12% |  |  | Applied to programme cash flows. Sensitivity sheet varies it 8%–20%.
Analysis horizon (years) | 5 |  |  | Fixed at 5 in the ROI layout.
Savings persistence, year over year | 85% |  |  | Share of an attributed saving still realised the following year. Optimisations erode: resources get re-provisioned, autoscaling floors drift up.
Programme cost
FinOps engineers (FTE) | 1.5 |  |  | Who runs the measurement and remediation.
Loaded annual cost per FTE | 180000 |  |  | Salary, benefits, overhead. Change to your organisation's rate.
Tooling and platform, per year | 60000 |  |  | Billing export, warehouse, watsonx.ai inference, workstation.
One-time setup (year 0) | 50000 |  |  | FOCUS export wiring, warehouse build, tagging remediation sprint.
Engineering hours per intervention | 16 |  |  | Executing a rightsizing, a storage migration or a cluster consolidation is engineering time. Counted once per event, in year 0.
Loaded engineering rate per hour | 150 |  |  | Blended senior/mid rate including overhead.
Year-1 ramp (share of run-rate realised in year 1) | 50% |  |  | Interventions land through the year; a linear ramp realises half the annual run-rate in year 1 and the full run-rate from year 2.
Planning
Budget growth assumption (annual) | 15% |  |  | Budget = run-rate of the first six months, grown monthly at this rate. Illustrates the method; a real plan replaces this row.
Months defining the run-rate budget | 6 |  |  | First N complete months average to the baseline. Fixed at 6 in the layout.
Attribution policy
Credit estimates that fail the parallel-trends check? | No |  |  | No = only estimates whose pre-trend check passed are credited (recommended). Yes = credit every identified estimate.
Scenario
Active scenario | Base |  |  | Drives ROI Analysis, Forecast and the KPI Dashboard. Scenario Analysis shows all three side by side regardless.
Scenario driver | Base | Bull | Bear | What it means
Effect realisation | 100% | 110% | 75% | Multiplier on attributed savings. Bear: a quarter of measured savings do not survive contact with production.
Programme cost multiplier | 1 | 0.9 | 1.3 | Bear: hiring takes longer and tooling costs more than planned.
Cloud growth (forecast) | 15% | 10% | 25% | Annual growth applied in the run-rate forecast.
Savings persistence | 85% | 90% | 70% | Overrides the financial assumption above when a scenario is active.
Active scenario values (formulas)
Effect realisation | 100%
Programme cost multiplier | 1
Cloud growth (forecast) | 15%
Savings persistence | 85%
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.

## 11 KPI Dashboard
KPI dashboard
Everything here is a formula into the other sheets. Change an assumption and the dashboard changes.
SIMULATED DATA. The estate is synthetic (FOCUS 1.2, 400 resources, 540 days). Figures illustrate the method; ground truth exists only because the data is simulated.
Annualised cloud run-rate |  | Events measured | Passing parallel trends | Credited annual savings
9422547.6934 |  | 117 | 103 | 1872634.0413
last 12 complete months, annualised |  | interventions with a usable control group | estimates credible enough to credit | identified, gated by parallel trends
Before/after would report |  | Programme NPV (5 yr) | ROI (PV basis) | Payback
1693741.0017 |  | 2833109.4303 | 186.3% | 6.5471
the industry's number |  | active scenario | active scenario | months
Budget variance, period |  | SIMULATED: gross misattribution | Active scenario | Attribution policy
7.198% |  | 450967.8445 | Base | parallel-trends gate
actual vs run-rate budget |  | ¦before/after − true¦, summed
Chart data (formulas)
Measure | Annual $
Before/after | 1693741.0017
Identified, all | 1809486.9023
Credited (gated) | 1872634.0413
SIMULATED true | 2020441.1259
Month | Budget | Actual
2025-07-01 | 697239.8145 | 723189.7249
2025-08-01 | 705407.9209 | 720339.0207
2025-09-01 | 713671.7161 | 726305.0112
2025-10-01 | 722032.321 | 791709.5642
2025-11-01 | 730490.8697 | 801718.1142
2025-12-01 | 739048.5095 | 856377.9119
2026-01-01 | 747706.4014 | 804605.0502
2026-02-01 | 756465.7198 | 708434.4292
2026-03-01 | 765327.6528 | 870094.2144
2026-04-01 | 774293.4027 | 880808.739
2026-05-01 | 783364.1856 | 837020.0112
Business unit | Budget | Actual
bu-assist | 1855728.944 | 2013844.9165
bu-checkout | 1017822.7468 | 1165464.9569
bu-datalake | 754985.3161 | 750185.8069
bu-datasci | 1773020.6852 | 1914114.7401
bu-platform | 838909.6998 | 841976.3948
bu-search | 1018337.7031 | 1113179.5295
unallocated | 876243.419 | 921835.4465